# Approach & Project Plan

Banking Campaigns Comparator – "Marketing Spy"

Two-week delivery plan  |  Monday 14 – Friday 25 September 2026

| Field | Value |
| --- | --- |
| Document | Approach & Project Plan v1.0 |
| Date | 14 September 2026 |
| Team | Siegried (project lead), Dan, Stephane |
| Client | ING Belgium – DACI / Customer AI (CAI) |
| Stakeholders | Diego Pardo y Cobo, Victor Onclinx |
| Duration | 10 working days: Mon 14 Sep – Fri 25 Sep 2026 |
| Companion document | ing_requirements.docx – Project Requirements Document (PRD) v1.0. Requirement IDs (FR-, DR-, LC-, NFR-, D-) used here refer to that document. |
| Delivery type | Proof of Concept. Comparator is committed; LLM campaign generation is a stretch goal. |

# 1. Purpose of this document

The PRD says what must be delivered. This document says how the team will get there in ten working days, who owns what, and what gets dropped first if time runs out.

Two decisions drive everything below:

The comparator is the commitment; generation is the bonus. — The committed MVP is: collect campaign pages, turn them into a structured dataset, profile each bank, position ING. The LLM campaign generator is built only once that chain runs end to end. This follows the ING brief directly — "start small, deliver end-to-end".

Ten days means one freeze gate, not continuous replanning. — At the end of Day 6 the team either has a working end-to-end comparator or it does not. That single decision point (section 6) decides whether the stretch goal is attempted.

# 2. The approach

## 2.1 The chain

Five steps, each producing an artefact the next one consumes. The value of the approach is that the same feature framework is used three times: to describe banks, to compare them, and — in the stretch — to evaluate what the LLM produces.

| # | Step | What happens | Artefact produced |
| --- | --- | --- | --- |
| 1 | Collect | Discover campaign pages through robots.txt and sitemaps, then snapshot them: HTML, full-page screenshot, image assets, provenance. | Raw snapshot store |
| 2 | Featurise | Turn every page into a row of features — text, colour, imagery, layout, value proposition — against one shared feature dictionary. | Campaign dataset + feature dictionary |
| 3 | Ground | Anchor the judgement-based features in established marketing frameworks rather than personal taste, so the scoring is defensible. | Scoring rubric |
| 4 | Profile & compare | Build a standard profile card per bank, then compare: ING vs peers, traditional vs challenger, similarity grouping. | Bank profiles + comparative analysis |
| 5 | Generate (stretch) | Prompt an LLM to produce a new campaign under explicit criteria, then score it with the same extractor from step 2. | Generated campaign + its feature scorecard |

## 2.2 Why the loop closes

Step 5 feeds back into step 2, and that is the part worth presenting. Because the generated campaign is scored by the same extractor as the real ones, the team can show where the generated campaign lands in the same feature space as the eight banks — "we asked for something more challenger-like, and here is the measurement showing it moved in that direction". That turns a subjective demo into a measured result, and it answers the stakeholders' question directly: "Can we prove it, measure it, and explain it?"

## 2.3 Guiding principles

Thin slice first. — One product family, one language, one page per bank, all the way through the chain by Day 6. Breadth is added afterwards, never before.

The schema is the contract. — The dataset schema is agreed on Day 2 and frozen. It lets collection, extraction and analysis proceed in parallel instead of in sequence — the only way three people fit ten days of work into ten days.

Compliance before code. — No page is fetched before its robots.txt has been read and recorded. This is a hard gate, not a task (LC-01 to LC-08).

Same yardstick for everyone. — ING is measured exactly as the competitors are (LC-09). Siegried reviews the ING section specifically for favourable framing.

Nothing is claimed that is not measured. — The team has no campaign performance data, so no design choice is said to cause better results. Recommendations are framed as hypotheses ING could test.

# 3. Team and roles

Three people, three workstreams that can run in parallel once the schema is frozen. Each person owns one stage of the chain end to end — they build it, they document it, and they present it in the technical session.

| Member | Role | Owns | Presents |
| --- | --- | --- | --- |
| Siegried | Project Lead & Marketing Framework Owner | • Scope decisions and the compliance note (D-01) • Sourcing the marketing principles and turning them into the scoring rubric (step 3) • Stakeholder contact and the Day 5 checkpoint • The business narrative: insights, recommendations, positioning story • Final quality gate: bias review, traceability of every claim | Business presentation (D-06) |
| Dan | Data Collection & Extraction Engineer | • Source discovery: robots.txt, sitemaps, URL shortlist (FR-02) • The scraping pipeline and the raw snapshot store (FR-03) • Automated feature extraction: text metrics, colour palettes, image and layout features (FR-04, FR-05) • Dataset build and data quality (FR-07, DR-01 to DR-10) • Repository hygiene, reproducibility of the pipeline (NFR-01, NFR-07) | Pipeline & data quality section (D-07) |
| Stephane | Analysis & Generative AI Lead | • Feature dictionary, co-designed with Dan and Siegried (FR-06) • Bank profile cards (section 4.2) • Comparative analysis: ING positioning, traditional vs challenger, similarity grouping (FR-08, FR-09) • All charts and visuals used in both presentations • Stretch: the LLM campaign generator and its evaluation (section 4.5) | Method, findings & limitations (D-07) |

Shared by all three — not delegated:

Rubric scoring. — Judgement-based features (tone, visual hierarchy) are scored independently by at least two people on a sample, and the disagreement is reported. One person scoring alone would not satisfy NFR-05.

Scope calls. — Any decision to add or drop a bank, a page or a feature is taken together at the daily standup and written into D-01.

The dry run. — Both presentations are rehearsed by the whole team on Day 9.

## 3.1 RACI by deliverable

R = responsible (does the work), A = accountable (answers for it), C = consulted, I = informed.

| Deliverable (PRD ID) | Siegried | Dan | Stephane |
| --- | --- | --- | --- |
| D-01 Scope & compliance note | R / A | C | C |
| D-02 Collection pipeline & snapshots | I | R / A | C |
| D-03 Feature dictionary | C | R | R / A |
| D-04 Campaign dataset | I | R / A | C |
| D-05 Analysis report | C | C | R / A |
| D-06 Business presentation | R / A | C | C |
| D-07 Data presentation | C | R | R / A |
| D-08 Repository & README | I | R / A | C |
| D-09 Limitations & next steps | A | C | R |
| Scoring rubric (marketing principles) | R / A | C | C |
| Bank profile cards | C | C | R / A |
| Generated campaign + scorecard (stretch) | C | C | R / A |

## 3.2 Ways of working

One repository, one branch per workstream. — Merged to main daily. No work sits uncommitted overnight.

Daily standup, 15 minutes, start of day. — What moved, what is blocked, what changes in scope.

The schema is frozen on Day 2. — After that, columns may be added but never renamed or removed without all three agreeing, because analysis code depends on them.

Sample data from Day 2. — Dan publishes five hand-collected rows in the agreed format on Day 2 so Stephane can start analysis code before the full scrape exists.

Decisions are written down the day they are taken. — A running decision log in the repository becomes most of D-01 and the limitations section for free.

# 4. The five steps in detail

## 4.1 Step 1 — Collect

Owner: Dan  |  Days 1–4  |  Delivers D-02

Read and archive robots.txt for each of the eight bank domains. Record what is allowed and disallowed for the user agent used. Any bank whose campaign pages are disallowed is dropped from scope and the drop is written into D-01 — not worked around (LC-01, LC-04).

Pull each sitemap and shortlist candidate campaign pages for the chosen product family (LC-02).

Fetch politely: rate-limited, honest user agent, each page fetched once and cached. Total request volume must stay negligible for the target site (LC-05).

Snapshot each page three ways — raw HTML, full-page screenshot, and the referenced image assets — with URL, timestamp and language attached (FR-03, DR-02, DR-06).

Render with a headless browser where pages are JavaScript-built, otherwise the layout and visual features will be wrong or empty.

Strip anything resembling personal data before storage (DR-09).

Hard gate: no page is fetched before its robots.txt has been read and recorded. A compliance breach invalidates the delivery no matter how good the analysis is.

## 4.2 Step 2 — Featurise, and the bank profile

Owners: Dan (extraction), Stephane (dictionary & profiles)  |  Days 2–6  |  Delivers D-03, D-04

Every page becomes one row. Features are split by how they are produced, because that determines how much they can be trusted:

| Type | Produced by | Examples | Trust |
| --- | --- | --- | --- |
| Automatic | Code, deterministic | Word count, readability, number of images, extracted colour palette, brand-colour share, page height, CTA count, animated assets present | High — reproducible exactly |
| Rubric-scored | A human against a written scale | Formality (1–5), benefit framing rational vs emotional, visual hierarchy clarity, persuasion levers used | Medium — report inter-rater disagreement |
| Model-assisted | LLM or vision model, prompt recorded | Imagery subject, tone classification, value-proposition summary | Medium — validate against human labels on a sample, report agreement |

The bank profile is the presentable form of the dataset: one standard card per bank, generated from the rows rather than written by hand, so it stays reproducible and comparable. The template is in Appendix A. This is what makes the comparison legible to the business audience — eight cards with identical fields, side by side.

## 4.3 Step 3 — Ground the scoring in marketing principles

Owner: Siegried  |  Days 1–5  |  Delivers the scoring rubric

The weakness of any design comparison is that "this page feels more persuasive" is one person's taste. The fix is to score against frameworks that already exist and are recognised, so that a reviewer can disagree with the score but not with the yardstick. Siegried sources the material and converts it into a rubric with defined levels — a definition and an observable indicator for every point on every scale.

| Framework | What it contributes to the rubric |
| --- | --- |
| AIDA (Attention, Interest, Desire, Action) | A structural checklist for a campaign page: does it do all four, in what order, and how much space does each get? |
| Cialdini's principles of persuasion | A closed list of persuasion levers to detect: social proof, scarcity, authority, reciprocity, commitment, liking. Turns "persuasive" into countable levers. |
| Feature–advantage–benefit framing | Distinguishes "3.2% gross annual rate" from "your money works while you sleep" — a measurable difference between traditional banks and challengers. |
| Value proposition framing | What is offered, to whom, against which alternative. Feeds the topics dimension of the PRD. |
| Visual hierarchy & F-pattern reading | Grounds the layout and attention features: what is above the fold, what the eye reaches first, CTA prominence and contrast. |
| Readability and plain-language standards | Objective backing for the tone dimension, and a known issue in Belgian banking communication. |

On sourcing the material: — use openly licensed or properly licensed sources — open courseware, published framework descriptions, books the team owns, free tiers of marketing training platforms. Course content is not redistributed inside the deliverables; it is cited. The same compliance posture applies here as to the scraping.

Timeboxed to two days of part-time effort. — The rubric only has to be good enough to score consistently. A perfect marketing theory is not a deliverable.

## 4.3 bis Banking-domain angles contributed by Siegried (added 14/09)

Additions to the marketing-framework input for step 3, on top of AIDA / Cialdini / FAB / value-proposition framing / visual hierarchy / readability above. Full definitions and feasibility notes are in the PRD, section 11 bis. Nothing above is removed — the team picks the v1 subset at standup.

Retail vs professional targeting, bancassurance bundle vs single product, rate architecture (base vs promo bonus), self-service vs advisor/branch CTA, switching-friction framing, prominence of regulatory disclosures, “free” framing with hidden conditions, Belgian fiscal calendar — candidate rubric dimensions grounded in retail-banking practice rather than generic marketing theory — see PRD 11 bis for the full definitions.

ESG claim specificity — recalibrated to “claim backed by a reference/figure vs adjective only”. (an explicit SFDR Article 6/8/9 read from the marketing page itself was considered and dropped as unrealistic — that classification lives in regulatory docs, not campaign pages)

Loyalty/referral mention — kept as the public-page proxy for retention/CRM strategy. (true CRM data is out of reach entirely (behind authentication, excluded by DR-01/DR-09), not a scoping choice)

Social media sentiment — documented as a D-09 next step, not added to the v1 scope. (this would reopen the scope-creep risk (R-07) the plan is explicitly built to avoid — flagged here rather than folded in silently)

Second pass, same day — institutional-backing trust signal (state ownership, tenure), capped/tiered rate presented as headline, youth/student lifetime-value acquisition, secondary-bank vs full-replacement positioning, expat/cross-border targeting, concrete green product vs generic ESG claim, branch/ATM network cited as a selling point — full definitions in PRD 11 bis.

Diminishing-returns note: likely the practical ceiling for this angle — each further dimension competes with the thin-slice principle and risk R-07 for the same limited time. The team's differentiator is expected to come from executing a smaller set of these with rigour and from the maturity of the business presentation, not from a ninth or tenth dimension.

## 4.4 Step 4 — Compare and position

Owner: Stephane  |  Days 5–8  |  Delivers D-05

ING versus each competitor, feature by feature: where ING is typical of its group and where it is an outlier (FR-09).

Traditional versus challenger: does the split the stakeholders assume actually appear in the data, and on which dimensions? This answers BO-02 directly.

Similarity grouping: cluster or distance the banks on the feature set and show which banks communicate alike — including whether ING lands with the traditional cluster or between the two (BO-03).

Verify the five deck observations in PRD section 2.4 one by one, with evidence, and say plainly where the eyeball impression does not hold (FR-14).

Small sample means descriptive, not inferential. Sample sizes on every chart; no significance claims.

## 4.5 Step 5 — LLM campaign generation (stretch)

Owner: Stephane  |  Days 7–8, only if the Day 6 gate passes  |  Delivers the generated campaign + scorecard

Attempted only after the comparator chain is complete. The point is not to produce pretty copy — it is to demonstrate that the feature framework is specific enough to drive and then measure a generation.

| Element | Definition |
| --- | --- |
| Input | Target product (the chosen family), target bank (ING), the ING profile card, the competitor profile cards, and the scoring rubric. |
| The criteria | An explicit target expressed in the project's own features — e.g. "ING tone of voice, but challenger-style visual density: word count in the bottom quartile, one hero image, two persuasion levers, CTA above the fold." |
| Two variants | A) On-brand: an ING campaign optimised against the rubric. B) Challenger-style: the same offer built with the patterns observed at Revolut, N26 and bunq. The contrast is the insight. |
| Output | Headline, subheading, body copy, call to action, colour and layout specification, and an image brief — not a finished creative. |
| Evaluation | Score both variants with the same extractor used on the real pages, and plot them against the eight banks. Show whether the generation landed where it was asked to. |
| Guardrails | Clearly labelled synthetic. No invented rates, prices or product terms — placeholders only. No competitor brand assets reused. Legal and risk disclaimers flagged as required but not drafted. Human review before anything is shown. |

If the Day 6 gate fails, this step is dropped in full and the criteria plus the prompt design are presented as "next step", not demonstrated. That is a planned outcome, not a failure.

# 5. Schedule — 10 working days

Mon 14 – Fri 25 September 2026. Highlighted rows are checkpoints.

| # | Date | Siegried | Dan | Stephane | Output by end of day |
| --- | --- | --- | --- | --- | --- |
| 1 | Mon 14 Sep | Frame scope: banks, product family, language. Start compliance review. | robots.txt + sitemaps for all 8 domains. | Draft feature dictionary v0. | Scope decision + compliance findings |
| 2 | Tue 15 Sep | Source marketing frameworks; start rubric. | Hand-collect 5 sample rows; agree schema. | Freeze schema with Dan; analysis skeleton on sample. | SCHEMA FROZEN + sample data |
| 3 | Wed 16 Sep | Rubric v1; write D-01 compliance note. | Scraper running on 3 banks; snapshot store. | Automatic feature extraction on samples. | First real snapshots |
| 4 | Thu 17 Sep | Rubric v1 tested on 2 pages. | All in-scope banks collected. | Extraction over full snapshot set. | Collection complete (D-02) |
| 5 | Fri 18 Sep | Stakeholder checkpoint; joint rubric scoring session. | Dataset v1 + data quality report. | Dataset v1 loaded; first comparison charts. | CHECKPOINT: dataset v1 (D-04) |
| 6 | Mon 21 Sep | Scores consolidated; bias review of ING rows. | Extraction hardened; pipeline re-run test. | Bank profile cards for all banks. | GATE: end-to-end chain works? |
| 7 | Tue 22 Sep | Insights and recommendations drafted. | Reproducibility check; README. | Full comparison + positioning. Stretch: generation criteria. | Analysis complete (D-05) |
| 8 | Wed 23 Sep | Business deck structure + narrative. | Repo tidy, dataset export (D-08). | Stretch: generate both variants and score them. | Stretch outcome known |
| 9 | Thu 24 Sep | Business deck complete (D-06). | Data deck: pipeline section. | Data deck: method and findings (D-07). | DRY RUN, both decks |
| 10 | Fri 25 Sep | Deliver business session. | Deliver technical section. | Deliver method and findings. | FINAL DELIVERY |

## 5.1 Milestones

| Milestone | When | Definition of done |
| --- | --- | --- |
| M1 – Scope and compliance fixed | End of Day 1 | Banks, product family and language chosen and written down; robots.txt findings recorded for every domain; any bank excluded on compliance grounds is named. |
| M2 – Schema frozen | End of Day 2 | Dataset columns agreed by all three; five sample rows exist in that format; analysis work can start without waiting for the scraper. |
| M3 – Collection complete | End of Day 4 | Every in-scope page snapshotted with HTML, screenshot, assets and provenance. Re-running collection is no longer on the critical path. |
| M4 – Dataset v1 | End of Day 5 | One row per page, all automatic features populated, missing values explained. Comparison work can proceed. |
| M5 – MVP gate | End of Day 6 | See section 6. |
| M6 – Analysis complete | End of Day 7 | ING positioned, banks grouped, deck hypotheses verified, at least three traceable insights written. |
| M7 – Dry run passed | End of Day 9 | Both decks presented start to finish to the team; every claim traced to a feature and a source page; timing checked. |
| M8 – Delivered | Day 10 | Both sessions delivered; repository re-runs from scratch. |

## 5.2 Meeting cadence

Daily standup — 15 minutes at the start of each day. Blockers and scope changes only.

Rubric scoring session — Day 5, all three, 90 minutes. Everyone scores the same two pages independently, then the disagreements are discussed and the rubric is tightened. This is what makes the scoring defensible.

Stakeholder checkpoint — Day 5, Siegried. Confirm scope, show dataset v1, and close the open questions carried in PRD section 17.

Gate review — Day 6, end of day, all three. Thirty minutes, one decision (section 6).

Dry run — Day 9, all three, both decks, full length.

# 6. The Day 6 gate

At the end of Day 6 the team asks one question: does the chain run end to end — from a URL to a scored, comparable row, to a bank profile, for every bank in scope?

| If the answer is | Then |
| --- | --- |
| YES | Days 7–8 attempt the LLM generation stretch. Stephane moves to generation; Siegried and Dan take over the remaining analysis and documentation so the comparator keeps progressing in parallel. |
| NO | The stretch is dropped immediately and without debate. Days 7–8 are spent completing and hardening the comparator. The generation idea is presented as a designed-but-not-built next step, with the criteria and prompt structure shown. |
| PARTIALLY — chain works for some banks only | Cut scope, not quality: drop the failing banks from the analysis, document why in D-01, and finish the comparator on what remains. The stretch is still dropped. |

The value of deciding this in advance is that it removes the temptation to keep a half-built generator alive at the cost of the committed deliverable. The stakeholders asked for a coherent, complete piece of work on a limited scope — a broken demo attached to an incomplete comparator is worse than no demo.

# 7. Dependencies and critical path

The critical path is: scope → compliance clearance → collection → dataset → analysis → decks. Everything else can slip a day without hurting the delivery.

| Dependency | Blocks | How it is de-risked |
| --- | --- | --- |
| Compliance clearance per bank | All collection for that bank | Done on Day 1 for all eight domains at once, before any scraping effort is invested. |
| Frozen schema | Analysis and profile code | Frozen Day 2 with five hand-made sample rows, so analysis never waits for the scraper. |
| Collection complete | Dataset, therefore all analysis | Thin slice first: one page per bank by Day 3, extra pages only after. A partial collection still yields a complete analysis. |
| Rubric v1 | Rubric-scored features | Automatic features are extracted independently, so a late rubric delays part of the dataset, not all of it. |
| Dataset v1 | Profiles, comparison, generation | Milestone M4 on Day 5 leaves two days of buffer before the gate. |
| Gate outcome | Days 7–8 plan for two people | Both branches are pre-planned, so no replanning time is lost on Day 7. |

# 8. Risks specific to this plan

Project risks that come from the ten-day constraint and the team shape. Analytical risks are covered in PRD section 16.

| ID | Risk | Mitigation | Owner |
| --- | --- | --- | --- |
| P-01 | A bank disallows collection, discovered late | All robots.txt checked on Day 1, before any effort is invested in that bank. | Dan |
| P-02 | Scraping consumes the whole first week | Timeboxed: one page per bank by Day 3. If a site resists, it is dropped, not fought. | Dan |
| P-03 | The stretch goal quietly eats the committed work | The Day 6 gate, decided by the whole team, and the stretch owner is the person whose committed work finishes first. | Siegried |
| P-04 | Schema churn forces analysis to be rewritten | Schema frozen Day 2; additions allowed, renames and removals only by unanimous agreement. | Stephane |
| P-05 | Rubric scoring turns into three different opinions | Joint scoring session on Day 5; disagreement measured and reported rather than hidden. | Siegried |
| P-06 | Single points of failure — one person ill for two days | Daily merges to main, a README kept current, and a written decision log mean any workstream can be picked up by another member. | Siegried |
| P-07 | Both decks left to the last two days | Deck skeletons created on Day 3 and filled as results arrive, not written at the end. | Siegried |
| P-08 | The generated campaign looks impressive and gets over-claimed | It is always presented next to its feature scorecard and labelled synthetic; no claim about real-world performance is made. | Stephane |

# 9. Decisions needed in the first two days

| # | Decision | Needed by | Owner | Default if unresolved |
| --- | --- | --- | --- | --- |
| 1 | Which product family anchors the comparison | Day 1 | Siegried | Term accounts — every bank runs one in September. |
| 2 | Which language is the reference | Day 1 | Siegried | One language used for all banks; the choice is recorded. |
| 3 | How many banks in the thin slice | Day 1 | All | Four: ING, two traditional peers, one neobank — the minimum that answers the traditional-vs-challenger question. |
| 4 | Is Belfius in scope | Day 1 | Siegried | Optional; included only if collection is straightforward. |
| 5 | Dataset schema and file format | Day 2 | Dan + Stephane | One CSV, one row per page, provenance columns first. |
| 6 | Which LLM for model-assisted features and generation | Day 2 | Stephane | One model, version recorded, prompts stored in the repository. |
| 7 | Repository visibility — public or internal | Day 2 | Siegried | Internal, given third-party brand assets are stored. |

# Appendix A — Bank profile card template

One card per bank, generated from the dataset. Identical fields for every bank, so the cards can be laid side by side in the business deck.

| Field | Content | Source |
| --- | --- | --- |
| Identity | Bank name, category (traditional / challenger), pages analysed, capture date. | Provenance columns |
| Palette | Dominant colours, brand-colour share, number of accent colours, where the accent appears (text / icons / imagery). | Automatic |
| Imagery signature | Photo, illustration or 3D; people present; lifestyle or product; static or animated. | Automatic + model-assisted |
| Layout archetype | Hero image or not; text and image adjacent or stacked; page length; elements above the fold. | Automatic |
| Tone | Word count, readability, formality score, address form, urgency markers. | Automatic + rubric |
| Value proposition | What is offered, how it is framed (rational or emotional), whether a rate or price is shown and how prominently. | Rubric + model-assisted |
| Persuasion levers | Which of the Cialdini levers appear, and how many. | Rubric |
| AIDA coverage | Which of the four stages the page covers, and the space each receives. | Rubric |
| One-line signature | The single sentence that distinguishes this bank from the others. | Written, evidence-backed |

# Appendix B — Generation brief and evaluation (stretch)

## B.1 What the generator is told

The product and the audience.

The target feature profile, expressed numerically where possible — word count band, image count, number of persuasion levers, CTA position, colour direction.

The brand constraints for the on-brand variant, taken from the ING profile card.

The competitor patterns for the challenger variant, taken from the neobank profile cards.

What it must not do: invent rates, prices or product terms; imitate a named competitor's assets; omit the placeholder for legal disclaimers.

## B.2 How the output is judged

| Criterion | How it is measured |
| --- | --- |
| Did it hit the target profile? | Run the same feature extractor over the generated campaign and compare the row to the requested target. This is the primary measure. |
| Is it distinguishable from the real ones? | Plot it alongside the eight banks in the feature space and see where it lands. |
| Is it usable? | Rubric-scored by the team on the same scales as the real pages — no separate, softer standard. |
| Is it safe? | Checked against the guardrail list: no invented figures, no borrowed assets, disclaimers flagged, labelled synthetic. |

The honest framing for the final presentation: this shows the feature framework is specific enough to steer and then measure a generation. It does not show that the generated campaign would perform better — the team has no performance data, and says so.

# Appendix C — What "done" looks like on Day 10

A repository that a stranger can clone and re-run to reproduce the dataset from the stored snapshots.

A dataset covering at least four banks including ING and at least one neobank, one row per page, every feature defined in the dictionary.

A profile card for every bank in scope, all with identical fields.

A clear answer to where ING stands, and whether it sits closer to traditional banks or challengers, with the features that support it.

At least three insights or improvement ideas, each traceable to a feature value and a source page.

A compliance note that answers "this is what we considered acceptable, and why".

A stated list of limitations: sample size, subjectivity, language, snapshot date, no performance data.

Two presentations delivered — one for the business, one for the data audience.

If the gate passed: two generated campaign variants with their feature scorecards. If it did not: the criteria and prompt design presented as the next step.